## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US 01 | Workflow Creation and Project Goal Document | MUST HAVE | Lucid Chart |  | 3- Completed
S2 | S2 | US 02 | Set up yfinance API; initialized repository and cleaned OHLCV historical data. Coded technical indicators: RSI, MACD, and SMA (Moving Averages). | SHOULD HAVE | yfinance, pandas, numpy,pandas, numpy | Kajal | 3- Completed
S3 | S3 | US 03 | Implemented data fetching & cleaning pipeline to retrieve OHLCV data for 60+ stocks using yfinance. Removed duplicates, handled missing values, and created clean datasets for feature generation. | MUST HAVE | yfinance, pandas, numpy | Kajal | 3- Completed
S4 | S4 | US 04 | Built feature engineering module to compute technical indicators (RSI, MACD, SMA) and additional derived features for model training. | MUST HAVE | pandas, numpy, python, matplotlib, seaborn | Kajal | 3- Completed
S5 | S5 | US 05 | Designed and implemented a separate data pipeline and integrated it into the team pipeline. Improved modularity and automation for better scalability. | MUST HAVE | Python, pandas, multiprocessing | Kajal | 3- Completed
S6 | S6 | US 06 | Optimized pipeline performance using parallel processing, reducing time for data fetching, cleaning, and feature computation. | MUST HAVE | multiThreadprocessing, | Kajal | 3- Completed
S7 | S7 | US 07 | Integrated Supabase for data storage & retrieval, enabling automated storage of cleaned data and feature tables for the ML models. | SHOULD HAVE | supabase, python-dotenv | Kajal | 3- Completed
S8 | S8 | US 08 | Built a Streamlit dashboard to visualize signals, monitor model performance, and track data drift. Added basic ML-Ops feedback loop for model monitoring. | SHOULD HAVE | streamlit,fastApi, pandas | Kajal | 3- Completed
S8 | S8 | US 08 (extra) | Prepared team presentation (PPT) and overall project documentation, including architecture diagrams, workflow, and key results. | MUST HAVE | PowerPoint, Markdown, Lucidchart | Kajal | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 81 | 17 | 15 | 13 | 5 | 7 | 6 | 6 | 4 | 2 | 2 | 2 | 1 | 1 | 1
SPRINT 1 BACKLOG
US 01 | 1 | Introduction to Technical indicators of stock | 2025-11-24 | 2025-11-26 | Manasi | others | completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 02 | 2 | Workflow creation(model deciding) | 2024-11-30 | 2025-12-03 | All | others | completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 03 | 3 | random forest and XG boost model creation | 2025-12-04 | 2025-12-11 | manasi | coding | completed | 12 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US 04 | 4 | created an hybrid ensembleengine code for all the Machine Learning Models | 2025-12-12 | 2025-12-18 | manasi | coding | completed | 12 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 05 | 5 | integration of LLM to the ML signal output to generate ai signals based on results | 2025-12-19 | 2025-12-26 | manasi | coding | completed | 12 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US 06 | 6 | creation of api and integration of api with dashboard | 2025-12-27 | 2026-01-07 | manasi | build and integration testing | completed | 12 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
US 07 | 7 | workflow optimization | 2026-01-09 | 2026-01-11 | All | build | completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 08 | 8 | Testing and deployment | 2026-01-12 | 2026-01-26 | manasi | integration testing | completed | 12 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S2 | 2025-12-05 | yfinance rate limits blocking bulk data downloads. | directly imported the yfinance library
S3 | 2025-12-10 | XGBoost model overfitting on small training sets. | Added Dropout layers and Early Stopping to the model.
S3 | 2025-12-12 | Merge conflicts when two people edited main.py. | Forced use of Feature Branches instead of pushing to main.
S4 | 2025-12-19 | Gemini API returning "Safety Filter" errors on trade talk. | Tuning the system prompt to avoid restricted financial keywords.
S5 | 2026-01-04 | Machine Learning signal error | increased run time and checked the api urls to be consistent

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-24 | 2025-11-30 | Manasi | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | S2 | 1-12-1025 | 2025-12-07 | Manasi | Use feature scaling (MinMaxScaler) before training LSTM. |  | Weekly documentation of technical indicators. | Keeps the final report drafting stress-free.
3 | S3 | 2025-12-04 | 2025-12-11 | Manasi | Catch bugs in XGBoost parameters early. | Committing large datasets or venv folders to GitHub. | Using Mail/Google chats for daily quick updates. | Maintain high communication for fast debugging.
4 | S4 | 2025-12-12 | 2025-12-18 | Manasi | Model evaluation metrics (adding Precision/Recall). | Hardcoding API keys (Gemini/Supabase) in scripts. | Move all credentials to a secure .env file. | Model evaluation metrics (adding Precision/Recall).
5
6
7